## Checklist
ID | Phase | Area | Topic | Action/Deliverable | Why (for your PhD) | Prior exposure | Priority | Suggested timing | Status | Evidence of completion | Key refs/resources | Notes
1 | P0 – Leverage existing strengths | Measurement / DT index | Construct definition & dimensions (Capability index) | Write a 2–3 page memo: what you did in DXC (BINA) and what 'good construct definition' looks like. | You already practiced defining dimensions (Business & Governance Alignment, Infrastructure/Data/Tech, People/Culture, Agility/Process) — turn it into an explicit transferable skill for your PhD work. | Strong | High | Month 0 | Done | Memo + 1 slide summary of dimensions | Your DXC dimensions and definitions in the DTI deck (BINA).
2 | P0 – Leverage existing strengths | Measurement / DT index | Needs index concept (pressure/urgency/intent) | Map the DXN (NUSA) idea to your PhD: 'multi-audience legitimacy pressures' as 'needs/pressure'. | You already framed 'need & pressure' and timing urgency; this becomes a bridge to legitimacy pressures in higher education. | Strong | High | Month 0 | Done | 1-page mapping note (DXN → legitimacy pressures) | DXN dimensions: Need strength, Urgency, Stakeholder demand, Ambition/intent.
3 | P0 – Leverage existing strengths | Measurement / DT index | Instrument design: indicators & survey items | Create a short checklist for writing survey items (clarity, single-idea, scale anchors) + examples from your index. | Your proposal includes a longitudinal survey; you can reuse your instrument-building muscle memory. | Strong | High | Month 0-1 | In progress | Reusable item-writing checklist + sample items | DTI deck sections on indicators and survey item lists.
4 | P0 – Leverage existing strengths | Measurement / DT index | Psychometrics pipeline (content/face validity → pilot → EFA/CFA → invariance) | Document your end-to-end validation pipeline as a template for the PhD survey strand. | Your index roadmap already includes validation steps and measurement invariance; formalizing it will speed up your PhD survey work. | Strong | High | Month 0-1 | In progress | Template 'measurement validation plan' (2 pages) | DTI deck psychometric validation timeline (content/face validity, pilot, EFA/CFA, invariance).
5 | P0 – Leverage existing strengths | Measurement / DT index | Index weighting approaches (PCA, Entropy, AHP, DEA) | Write a 1-page 'when to use what' note + assumptions/limitations for each method. | Even if your PhD isn't an index, this trains you to justify operationalization and weighting/aggregation choices (important in management research). | Intermediate | Medium | Month 1 | Not started | Comparative note + example calculation in Excel/R | DTI deck lists PCA/Entropy/AHP/DEA and rationale snippets.
6 | P1 – Foundations | Research foundations | What counts as a contribution in management research | Read 2–3 classic pieces on 'theoretical contribution' and write a 1-page 'contribution claim' for your project. | Management PhD evaluation is theory contribution-first; you need to state clearly: phenomenon → gap → mechanism → contribution. | New | High | Month 0-1 | Not started | 1-page contribution statement | Look up: theory contribution in management (journal editorials; PhD handbook).
7 | P1 – Foundations | Research foundations | Paradigms & philosophy of science (positivist/interpretivist/critical, etc.) | Make a 'stance' note: where your project sits (process/interpretive with complementary survey). | Helps you defend method choices (process study + survey) and write the methodology chapter coherently. | New | Medium | Month 1 | Not started | 1–2 page stance note | Intro texts on philosophy of social science; IS research methods overviews.
8 | P1 – Foundations | Academic craft | Reading for theory (how to read management papers) | Create an 'annotated reading template' (question, constructs, mechanism, boundary conditions, methods). | You’ll process a large literature base (temporal structuring, legitimacy, GenAI/assessment) efficiently. | New | High | Month 0 | In progress | Reusable template in Notion/Word | Use it for the first 10 papers immediately.
9 | P1 – Foundations | Academic craft | Academic writing in management (argument structure) | Write a 1-page 'storyline' for your proposal: phenomenon → puzzle → theory → method → contribution. | Your proposal is already strong; this turns it into publishable framing. | Intermediate | High | Month 0-1 | In progress | 1-page storyline + 10-slide talk outline | Use your current abstract and RQs as starting point.
10 | P2 – Core theory deep-dive | Theory | Temporal structuring (Orlikowski & Yates) — concepts & how to operationalize | Build a concept map: rhythms, pacing, deadlines, 'what counts as progress', temporal regimes; list observable indicators in universities. | Your project uses temporal structuring as overarching lens; you need to move from citation → analytic toolkit. | Intro | High | Month 1 | Not started | Concept map + 2-page operationalization note | Your proposal states time is enacted through recurrent practices (temporal structuring).
11 | P2 – Core theory deep-dive | Theory | Organizational legitimacy (Suchman) — pragmatic/moral/cognitive + multi-audience | Write a 'legitimacy matrix' for students/parents/employers: what each audience values; what evidence they accept; likely conflicts. | Your proposal foregrounds multi-audience legitimacy in higher education; this matrix guides sampling and analysis. | New | High | Month 1 | Not started | Legitimacy matrix + interview probes | Proposal highlights triadic audiences (students/users, parents/payers, employers/validators).
12 | P2 – Core theory deep-dive | Theory | Sociomateriality (Orlikowski) — using it without 'tech as factor' | Create a memo: what 'entanglement' means in your setting (AI tools, rubrics, LMS logs, policies, classroom practices). | Needed to theorize why 'adding AI' reconstitutes assessment artifacts and interaction, as you argue. | Intro | High | Month 1-2 | Not started | 2-page sociomaterial memo + list of artifacts to collect | Proposal frames educational work as sociomaterial and entangled.
13 | P2 – Core theory deep-dive | Theory | Algorithmic management & contested control (Kellogg et al.) | Identify 3–5 'control points' in universities (proctoring, detection, AI feedback, dashboards) and potential resistance tactics. | You link AI proctoring/detection/feedback to new control and resistance dynamics; you need concrete analytic categories. | New | Medium | Month 2 | Not started | Control-point map + coding sensitizing concepts | Proposal notes AI standardizes evaluation/visibility reshaping control/resistance.
14 | P2 – Core theory deep-dive | Theory | Signaling theory (Spence) applied to degrees under GenAI | Write a 1–2 page note: what signals are at risk, what alternative signals may emerge (authentic assessment, portfolios, proctored tasks). | Your legitimacy argument includes degrees as signals; you need to connect signal credibility to assessment redesign. | New | Medium | Month 2 | Not started | Signal map + implications for cases | Proposal links credential trust to signaling and risk of inflated competence.
15 | P2 – Core theory deep-dive | Theory building | Mid-range theory & mechanisms (from process data) | Practice: write 3 candidate mechanisms for 'fast but hollow' vs 'durable bridges' and what evidence would support each. | Your intended output is a mid-range theory of temporal legitimacy; mechanism thinking is the core skill. | New | High | Month 2-3 | Not started | Mechanism table (hypothesis-like, but qualitative) | Proposal aims for mechanism-based explanation and mid-range theory.
16 | P2 – Core theory deep-dive | Theory building | Define and refine your new construct: Flashpoint Bridgework | Draft a construct definition + dimensions (re-timing, re-authoring, re-legitimating) and boundary conditions. | This is your signature contribution; it must be crisp and distinguishable from adjacent constructs. | Intro | High | Month 2-3 | Not started | Construct definition + 1-page nomological network | Proposal lists bridgework visibility in re-timing/re-authoring/re-legitimating practices.
17 | P3 – Domain literature | Higher education studies | Higher education as an organizational field (governance, quality assurance, professional bodies) | Build an annotated map of key stakeholders and institutional constraints in your target contexts (UK + emerging economy). | Your cases sit inside a regulated field; legitimacy is shaped by accreditation, QA, and professional norms. | New | High | Month 1-2 | Not started | Stakeholder map + 1-page field note per context | Start from your triadic audience framing in the proposal.
18 | P3 – Domain literature | Higher education studies | Assessment regimes & academic integrity governance | Collect and compare 5–10 university AI/assessment policies; code what counts as acceptable assistance, evidence, and fairness. | Bridgework is likely visible in policy texts and enforcement practices (integrity cases). | New | High | Month 2-3 | Not started | Policy corpus + initial codebook | Proposal includes institutional artifacts: policies, guidelines, rubrics, integrity cases.
19 | P3 – Domain literature | Higher education studies | Learning analytics / LMS as sociotechnical infrastructure | Identify what 'digital traces' exist (LMS logs, submission history, feedback tools) and ethical access routes. | Your design mentions digital traces; you’ll need to know what's realistic and how to interpret traces. | New | Medium | Month 3 | Not started | Trace inventory + ethics considerations list | Proposal mentions LMS logs/workflow documents/anonymized assessment iterations.
20 | P4 – Domain literature | GenAI & learning/assessment | Generative AI in learning: promises vs failure modes | Create a 2-page synthesis: support (personalization/materials) vs risks (validity, ethics, 'false mastery'). | This grounds your phenomenon and helps you design interview prompts that go beyond 'cheating'. | Intro | High | Month 1 | Not started | 2-page synthesis + 10 key citations list | Proposal frames GenAI as both promising and disruptive; risk of 'false mastery'.
21 | P4 – Domain literature | GenAI & learning/assessment | Epistemic agency (assessment–knowledge–society link) | Operationalize 'epistemic agency' for your study: behaviors, responsibilities, discourse markers; propose how to observe it. | Your bridgework aims to protect/enable epistemic agency; you need an observable definition for analysis. | New | High | Month 2 | Not started | Operational definition + indicators table | Proposal discusses epistemic agency at risk when cognition is outsourced.
22 | P4 – Domain literature | GenAI & learning/assessment | Authentic assessment design & redesign patterns | Compile a pattern library: in-class drafting, oral defenses, iterative drafts, reflection, portfolios, group work, etc. + pros/cons. | Bridgework often shows up in assessment redesign; you need a vocabulary to describe variants and tradeoffs. | New | High | Month 2-3 | Not started | Assessment pattern library (1–2 pages) | Linked to re-timing and re-authoring practices in your construct.
23 | P4 – Domain literature | GenAI & learning/assessment | Academic integrity & detection/proctoring: limits and unintended effects | Summarize major arguments: false positives, equity, surveillance, trust; note what your study will/won’t claim. | Prevents the project from being pulled into tech-deterministic debates; keeps focus on legitimacy and time. | New | Medium | Month 3 | Not started | 1-page boundary note + ethics checklist | Proposal notes contested terrain around AI proctoring/detection/feedback.
24 | P5 – Positioning in IS/DT | Information Systems / Digital transformation | Digital transformation theory basics (beyond adoption): sociotechnical change, organizing, capabilities | Write a short 'DT positioning' paragraph for your paper: how your study extends DT accounts by adding temporal legitimacy. | Your proposal critiques DT accounts that assume speed is beneficial; you need to position clearly in IS/DT literature. | Intermediate | High | Month 1-2 | Not started | Revised positioning paragraph + candidate target journals list | Proposal identifies a gap: speed treated as beneficial; legitimacy assumed to follow.
25 | P5 – Positioning in IS/DT | Information Systems / Digital transformation | Dynamic capabilities vs sociomaterial/process views (when each helps) | Make a compare-contrast table: what each explains, where it fits your argument, and avoid mixing logics. | You’ve used Dynamic Capabilities & Sociotechnical Systems in your index work; align that experience with your new theorizing choices. | Intermediate | Medium | Month 2 | Not started | 1-page comparison table | DTI deck uses Dynamic Capabilities and Sociotechnical Systems as theory anchors.
26 | P6 – Methods (Qual) | Qualitative methods | Process research & longitudinal case study design | Design note: case selection logic, number of cases, access strategy, and what counts as a 'flashpoint event'. | Your study is explicitly longitudinal multi-case process; design quality is judged hard in management journals. | New | High | Month 1-2 | Not started | Case design memo + sampling frame | Proposal: longitudinal multi-case process study (3–5 universities) and identify flashpoint events.
27 | P6 – Methods (Qual) | Qualitative methods | Interviewing multiple audiences (students, faculty, admins, parents/employers) | Draft 3 tailored interview guides + recruitment scripts + consent language. | Multi-audience legitimacy is central; you need instruments that elicit differences without leading respondents. | New | High | Month 2-3 | Not started | Interview guides + pilot interviews notes | Proposal lists interviews across faculty/students/admins and (where feasible) parents/employers.
28 | P6 – Methods (Qual) | Qualitative methods | Observation of classrooms/assessment as temporal practice | Create an observation protocol focusing on pacing, deadlines, AI use moments, feedback loops, authoring negotiations. | Temporal structuring requires you to 'see time' in practice; observation protocol is the bridge. | New | High | Month 3 | Not started | Observation protocol + fieldnote template | Proposal includes classroom & assessment observations (time and interaction enacted).
29 | P6 – Methods (Qual) | Qualitative methods | Document & artifact analysis (policies, rubrics, integrity cases) | Set up a document coding scheme aligned to re-timing/re-authoring/re-legitimating. | Artifacts are a major data source and often contain explicit legitimacy language. | Intro | High | Month 3 | Not started | Artifact codebook + coded sample (10 docs) | Proposal lists institutional artifacts as a key data source.
30 | P6 – Methods (Qual) | Qualitative methods | Abductive analysis (iterate between data and theory) | Create an analysis workflow: initial coding → memos → theoretical sampling → second-cycle coding; define memo types. | Your proposal commits to abductive analysis; you need a repeatable workflow to avoid getting lost in data. | New | High | Month 3-4 | Not started | Analysis plan + 3 example memos | Proposal: abductive analysis iterating between data and theory.
31 | P6 – Methods (Qual) | Qualitative methods | Temporal data strategies (event sequencing, narratives, visual maps) | Practice with a small dataset: build a timeline, identify episodes, and link to legitimacy judgments. | Your theory is about time; using explicit temporal analytic techniques strengthens the paper. | New | Medium | Month 4 | Not started | Timeline template + example from pilot | Aligned with temporal structuring lens.
32 | P7 – Methods (Quant) | Quantitative methods | Longitudinal survey design (waves, panel retention, measurement invariance) | Draft survey wave plan: timing, constructs, attention checks, and invariance strategy across audiences. | Your proposal includes a longitudinal survey with students/staff/(employers) and panel techniques; design errors are costly. | Intermediate | High | Month 2-3 | Not started | Survey blueprint (waves, sampling, logistics) | Proposal outlines longitudinal survey across stakeholder groups and panel/regression analysis.
33 | P7 – Methods (Quant) | Quantitative methods | Scale development & validation (deep dive) | Extend your psychometric pipeline: item response theory basics, reliability, validity types, CFA/SEM reporting standards. | You already have a pipeline from index work; deepen to PhD-level rigor for publication. | Intermediate | High | Month 3-5 | Not started | Measurement model report template + simulated example | DTI deck mentions IRT, EFA/CFA, internal consistency, ICC/rWG, invariance.
34 | P7 – Methods (Quant) | Quantitative methods | Panel / longitudinal regression basics | Learn fixed/random effects intuition, clustered SE, and basic panel diagnostics; write an analysis plan for your variables. | Your proposal mentions regression and panel-based techniques; you need to know what claims are defensible (you already state non-causal). | New | Medium | Month 4-6 | Not started | Analysis plan + small replication exercise | Proposal: panel/regression to explore associations (not causal).
35 | P7 – Methods (Quant) | Quantitative methods | Multilevel data (students nested in courses/universities) — when you need it | Decide whether your survey requires multilevel modeling and what minimum sample structure is needed. | HE data often nests; ignoring this can bias inference. You need an explicit choice. | New | Medium | Month 5-6 | Not started | Decision note + power/feasibility check | Relevant given multi-case universities and multiple stakeholder groups.
36 | P7 – Methods (Quant) | Quantitative methods | Visualization & reporting (tables/figures for management journals) | Create templates for descriptive stats, construct validity tables, and key plots. | Speeds up paper writing later and reduces last-minute formatting stress. | Intermediate | Low | Month 6 | Not started | Reusable table/figure templates | Journal style guides (AMJ/OS/ISR etc).
37 | P8 – Integration | Mixed methods | Qual–quant triangulation strategy | Write a 1–2 page integration plan: which constructs are shared, how survey informs case comparisons, and what 'convergence' looks like. | Your survey is meant to triangulate process analysis; reviewers will ask how the strands talk to each other. | New | High | Month 3-4 | Not started | Integration memo + joint display table skeleton | Proposal explicitly says the quant strand triangulates and strengthens theory development.
38 | P8 – Integration | Mixed methods | Case comparison logic (cross-case analysis) | Define cross-case dimensions (e.g., policy stance, assessment design intensity, AI governance maturity) and how they relate to outcomes. | Needed to explain variation: when institutions become 'fast but hollow' vs 'durable bridges'. | New | High | Month 6-12 | Not started | Cross-case comparison framework | Proposal aims to explain when outcomes differ across cases.
39 | P9 – Execution & impact | Ethics / governance | Research ethics in HE (student privacy, power asymmetry, AI disclosure) | Draft ethics protocol: consent, anonymity, data minimization, handling integrity cases, and AI-use disclosure rules for participants. | Your proposal flags these as core ethical concerns; ethics approval can be a schedule bottleneck. | New | High | Month 1-2 | Not started | Ethics application draft + risk register | Proposal notes privacy, disclosure, and power asymmetries.
40 | P9 – Execution & impact | PhD management | Project management: year-by-year plan & weekly system | Translate your proposal timetable into a weekly rhythm: reading, writing, data, analysis; set review cycles. | Temporal structuring applies to your own PhD too—this keeps momentum without burnout. | New | Medium | Month 0 | In progress | 12-week plan + recurring review checklist | Proposal includes a year 1–3 timetable outline.
41 | P9 – Execution & impact | Publishing / career | Target journals & paper roadmap (1–3 papers) | Choose 1 primary outlet for the main theory paper + a methods/measurement or education-focused outlet; outline paper packages. | Helps you read with purpose and collect data that fits the genre expectations. | New | Medium | Month 2 | Not started | 1-page publication plan | Align with your stated mid-range theory goal.
42 | P9 – Execution & impact | Impact / stakeholders | Translate theory to guidance (policy makers, QA bodies, employers) | Draft an 'impact brief' outline: what universities should do during AI flashpoints; what evidence supports it. | Your proposal targets societal contribution and guidance on what credentials certify; impact writing is a separate skill. | New | Low | Month 12+ | Not started | 2-page impact brief draft | Proposal states societal contribution re: what degrees certify in AI-saturated world.

## Dashboard
Brilly – PhD Learning Roadmap Dashboard
Metric | Value | Status | Count
Total items |  | Done
Done |  | In progress
In progress |  | Not started
Not started |  | Blocked
Blocked
% Done

## Reading List
Area | Key reading (starter set) | Why it matters here | How to read / questions
Temporal structuring | Orlikowski & Yates (2002) – Temporal structuring | Core lens: time as enacted through practices/structures. | What are the recurrent practices? What temporal regimes become authoritative?
Legitimacy | Suchman (1995) – Managing legitimacy | Backbone: pragmatic/moral/cognitive legitimacy across audiences. | What legitimacy claims are made? By whom? With what evidence?
Sociomateriality | Orlikowski (2007) – Sociomaterial practices | Avoid 'AI as tool' framing; focus on entanglement of tech & practice. | What artifacts/practices co-constitute assessment?
Algorithmic management | Kellogg, Valentine & Christin (2020) – Algorithms at Work | Frames control/resistance when evaluation becomes algorithmic. | Where are metrics/visibility/standardization introduced? What resistance?
Signaling | Spence (1973) – Job market signaling | Degrees as signals; GenAI threatens signal credibility. | What makes a signal credible? What new signals could substitute?
Process research | Langley (1999) – Strategies for theorizing from process data | Toolbox for longitudinal analysis (temporal bracketing, narrative, etc.). | Which strategy fits your dataset? How will you represent time?
Case study design | Eisenhardt (1989) / Yin (case study guidance) | Case logic, replication, rigor, and boundary conditions. | What is your theoretical sampling logic? What is a 'case'?
Mixed methods | Creswell (mixed methods) + joint displays | Explains integration logic between qual and quant strands. | How will survey results triangulate your process theory?
GenAI & learning | Key articles you already cite (Yan 2024; Larson 2024; integrity/epistemic agency) | Phenomenon base: promises and challenges for learning/assessment. | What is 'false mastery'? Which risks are legitimacy-relevant?